## Sheet 1 - UNISQ EEG DATA RESEAR
UNISQ EEG DATA RESEARCH PLATFORM
WBS LEVEL | DESCRIPTION | RESOURCE | START DATE | END DATE
1 | Project: Enhancing the UniSQ EEG Data Research Platform | Team | 16 September 2024 | 22 November 2024
1.1 | Phase 1: Planning and Requirements Analysis | Team • Client | 16 September 2024 | 20 September 2024
1.1.1 | Define Project Scope and Objectives | Team Client | 16 September 2024 | 17 September 2024
1.1.2 | Requirements Gathering and Analysis | Team Client | 17 September 2024 | 18 September 2024
1.1.3 | Develop Initial Project Plan | Brendan Team | 19 September 2024 | 20 September 2024
1.2 | Phase 2: Design and Prototyping | Team | 23 September 2024 | 27 September 2024
1.2.1 | High-Level System Architecture Design | Subin Deshaja Brendan | 23 September 2024 | 25 September 2024
WBS LEVEL | DESCRIPTION | RESOURCE | START DATE | END DATE
1.2.2 | New UI/UX Design | Subin Deshaja Aditya | 24 September 2024 | 25 September 2024
1.2.3 | New Features Design | Subin Deshaja Meenu | 25 September 2024 | 27 September 2024
1.3 | Phase 3: Core Feature Development | Subin Deshaja | 30 September 2024 | 08 November 2024
1.3.1 | Sprint 1: Implement Search and Sort Functionality | Subin Deshaja Brendan | 30 September 2024 | 04 October 2024
1.3.2 | Sprint 2: Implement Abstract Expansion Feature | Subin Deshaja Aditya | 07 October 2024 | 11 October 2024
1.3.3 | Sprint 3: Develop Email-Based Approval System | Subin Deshaja Meenu | 14 October 2024 | 18 October 2024
1.3.4 | Sprint 4: User Interface Enhancements | Subin Deshaja Brendan | 21 October 2024 | 25 October 2024
1.3.5 | Sprint 5: Implement Mobile Compatibility | Subin Deshaja | 28 October 2024 | 08 November 2024
1.3.6 | Sprint 6: Secondary Feature Development (If Time Permits) | Subin Deshaja Meenu | 8 November 2024 | 15 November 2024
1.4 | Phase 4: Testing and Quality Assurance | Subin Meenu | 11 November 2024 | 15 November 2024
1.4.1 | Integration Testing | Subin Deshaja | 11 November 2024 | 12 November 2024
1.4.2 | System Testing | Subin Deshaja Brendan | 13 November 2024 | 14 November 2024
1.4.3 | User Acceptance Testing (UAT) | Subin Meenu | 14 November 2024 | 15 November 2024
1.5 | Phase 5: Deployment and Finalisation | Brendan | 18 November 2024 | 22 November 2024
1.5.1 | Finalize Documentation and Knowledge Transfer | Subin Deshaja Aditya | 18 November 2024 | 19 November 2024
1.5.2 | Final Deployment | Subin Deshaja | 20 November 2024 | 21 November 2024
1.5.3 | Conduct Final Presentation and Client Sign-Off | Team | 22 November 2024 | 22 November 2024